## Sheet1
| Project Name | Graduate Teaching Assistant Management System for North University
| Role | Front End Development
Project Planning
Task Description | Start Date | End Date | Duration (days)
Project Kick off | 2023-03-09 | 2023-10-09 | 7
Requirement Analysis | 2023-11-09 | 17/9/2023 | 7
System Design | 18/9/2023 | 24/9/2023 | 7
Setup the database | 25/9/2023 | 29/9/2023 | 5
Setup the environment | 30/9/2023 | 2023-04-10 | 5
Create Project | 2023-05-10 | 2023-07-10 | 3
Implement User Interfaces | 2023-08-10 | 24/10/2023 | 15
Integrate UI Components | 25/10/2023 | 2023-10-11 | 16
Conduct Unit Testing | 2023-11-11 | 15/11/2023 | 5
Integration Testing | 16/11/2023 | 20/11/2023 | 5
User Acceptance Testing | 21/11/2023 | 25/11/2023 | 5
Bug Fixes | 26/11/2023 | 2023-05-12 | 10
Project Deployement | 2023-06-12 | 2023-08-12 | 3
Documentation | 2023-09-12 | 2023-12-12 | 4