## Sheet1
| Project Name | Graduate Teaching Assistant Management System for North University
| Role | Front End Development
Project Planning
Task Description | Start Date | End Date | Duration (days)
Project Kick off | 2024-01-23 | 2024-01-24 | 1
Requirement Analysis | 2024-01-25 | 2024-01-26 | 2
System Design | 27/01/2024 | 05/02/2024 | 10
Setup the database | 06/02/2024 | 10/02/2024 | 5
Setup the environment | 11/02/2024 | 15/02/2024 | 5
Implement User Interfaces | 16/02/2024 | 25/02/2024 | 10
Integrate UI Components | 26/02/2024 | 06/03/2024 | 10
Create database models | 07/03/2024 | 21/03/2024 | 15
Authentication system | 22/03/2024 | 2024-03-26 | 5
Write backend urls and logic | 27/03/2024 | 15/04/2024 | 20
Bug Fixes | 16/04/2024 | 25/04/2024 | 10
Project Deployement | 26/04/2024 | 28/04/2024 | 3